## Project Backlog
User Story | Priority | Workload (hrs) | Dev | Sprint Goals
Allow users to choose between learning/practice mode | LOW | 1 |  | Basic UI
Allow users to pick an ingredient | HIGH | 4 |  | Store recipies
Allow users to measure ingredient | MED/HIGH | 3 |  | Deterrmine pouring method (Box2d)
Allow users to pour ingredients | HIGH | 2025-02-06 |  | Add shaking (button)
Picking different ingredients
Allow user to mix/shake ingredients | LOW | 2
Allow user to submit drink | MED | 1
Allow user to trash the drink (start over) | LOW | 1
As a user, I want my drink to be scored | MED | 2
Allow user to view recipes in Learning Mode | MED/HIGH | 1

## Sprint 1 Backlog
Sprint 1 Backlog
Sprint Goal:
User Story | Task | Workload (hrs)
Allow users to pick an ingredient | Create GUI shelf for all the ingredients to sit on | 0.5
| Create GUI buttons for each ingredient | 0.5
| Spawn in a physics-based version of the designated ingredient when the user clicks it | 1
| Destroy any previous physics-based ingredient if it is already out | 0.5
Allow users to pick up physics ingredients | Make physics based ingredient object | 2
| Detect when user clicks and drags ingredients | 1
| Move physics ingredient to the mouse | 2
Allow users to measure ingredient | Detect when a user drags an ingredient onto a the jigger tool | 2
| Show measuring dialogue | 1
| Store entered value from measuring dialogue | 0.5
| Play sound to indicate that the action was completed | 0.5
| Change jigger appearance to indicate the action was completed | 1
| Update jigger properties | 0.5
Allow users to pour ingredients | Detect when a user drags an ingredient onto a the mixer or drink tool | 2
| Play sound to indicate that the action was completed | 0.5
| Update mixer properties | 0.5